## Sheet1
CCTT/TT Meetings Action Log (last updated 7 April 2023)
|  |  | 29 |  |  | 15
Action | Date Raised | Actionee | Open/Closed (as noted by CCTT FEB23) | Comment | Tram Team Response | New Status (as noted by TTN MAR23) | CCTT Comment on new status
Ground born noise - review and issue report | 2021-01-01 | TT/RL | Closed |  | N/A | Closed
Leopold Place crossing issues - raise with SfP team | 2021-01-01 | TT/RA | Closed |  | N/A | Closed
Send drawings of final design regarding vibration issues | 2021-02-01 | TT/RL | Closed |  | N/A | Closed
Tram traffic modelling - provide responses and final modeling results | 2021-02-01 | TT/SJ | Open | List of questions regarding modelling | TBD March meeting | Open
Lighting issues - escalate witin CEC and report back | 2021-02-01 | TT/RA | Closed |  | N/A | Closed
TRO Tram Route - hold meetings with CCTT members | 2021-02-01 | TT/RA | Closed |  | N/A | Closed
Provide list of questions on GBN/V Report | 2021-03-01 | CC/MB | Closed |  | N/A | Closed
Arrange meeting with CEC street lighting team tio discuss CCTT concerns | 2021-03-01 | TT/RA | Closed |  | N/A | Closed
Noise and vibration impact of traffic on diversion streets - investigate and report back | 2021-04-01 | TT/RA | Open |  | TBD March meeting | Open
Traffic management issues (Picardy Place and Easter Road) - investigate and report back | 2021-04-01 | TT/RA | Closed |  | N/A | Closed
Issue summary of meetings with CC members regarding TRO | 2021-04-01 | TT/RA | Closed |  | N/A | Closed
Issue copy of NTBCC comments regarding TRO to TT | 2021-04-01 | CC/MB | Closed |  | N/A | Closed
Respond to issues raised in above report | 2021-04-01 | TT/SJ | Closed |  | N/A | Closed
TRO London Road /Leith Walk - provide clarity on process | 2021-04-01 | TT/RA | Closed |  | N/A | Closed
Access to APOG minutes - investigate and report back | 2021-05-01 | TT/CW | Open |  | TBD March meeting | Open
Traffic modelling - arrange presentation of results | 2021-08-01 | TT/SJ/RA | Open | Also raised at Sept 2021, Oct 2021, Nov 2021 and May 2022 meetings | TBD March meeting | Open | Suggest close as duplicate action
Issue final drawings of public realm along Trams route | 2021-09-01 | TT/RL | Open | Also raised at November 2021 meeting | Landscaping drawings are on the ETYN website | Closed | Agreed complete - this action related to the distribution of hard copy versions of plans which has been completed
TRO Melrose Drive junction - raise traffic management concerns with TMRP | 2021-09-01 | TT/RA | Open |  | Completed and no concerns from TMRP, LB or emergency services | Closed | Agreed complete - do you have a date or confirmation that these concerns were included in approval of TRO?
Noise and Vibration surveys - arrange for CCTT to meet with ET | 2021-09-01 | TT/RL | Open | To be arranged once operations planned | TBD March meeting | Open
Visibility and accessibility of temporary pedestrian crossings - improve signage | 2021-09-01 | TT/SJ | Closed |  | N/A | Closed
Final Landscape designs - arrange meeting with CC representatives | 2021-10-01 | TT/RA | Closed |  | N/A | Closed
Elm Row public realm final design issues - provide summary of CC concerns | 2021-10-01 | CC/MB | Closed |  | N/A | Closed
Width of loading bays along Leith Walk - provide technical note justifying designs | 2021-10-01 | TT/RA | Open |  | Previously provided | Closed | Agreed complete - are you able to provide copy of the technical note?
Pavement widths - provide table for Leith Links area | 2021-10-01 | TT/RA | Open | Note issued showing where pavements were less than 2m wide for whole route | Footpath widths attached | Closed | Agreed complete
Provide list of planned repairs of potholes and other damage to diversion routes | 2021-10-01 | TT/RA | Open | Incorrecty shown in the minutes to be actioned by CC/MB | CEC Roads team and can be reported via usual routes on CEC website | Closed | Do not agree that this can be closed. There was an action on RA to compile list based on reports submiutted to trams team
Need to establish register of legacy issues | 2022-02-01 | TT/RL | Open |  | CCTT Tracker | Closed | Do not agree that this can be closed. Has CCTT tracker been populated?
Discuss Gayfield Square traffic management issues | 2022-03-01 | TT/RA, CC/MB | Closed |  | N/A | Closed
Provide regular updates on impact on businesses and funding | 2022-03-01 | TT/CW | Closed |  | N/A | Closed
Confirm location/design of communal bin hubs within Tram project boundaries | 2022-04-01 | TT/RA | Open |  | Provided to HT previously and hub locations on landscaping plans on ETYN website | Closed | Agreed complete
Contact BT to seek improvements toretained phone boxes | 2022-04-01 | CC/HT | Open |  | Phone boxes removed as part of site clearance | Closed | Agreed complete - do we have a list of the phone boxes that wil be removed and those that will be retained?
Clarify agreed design for active travel elements of Trams project | 2022-05-01 | TT/RA | Open |  | More detail required to answer question | Open | Suggest close unless further detail can be provided
Chase response from Gareth Barwell on asset handovers | 2022-05-01 | CC/HT | Closed |  | N/A | Closed
Location of planned bus shelters along the route - provide drawings | 2022-07-01 | TT/RA | Open | Also raised at October and December 2022 meetings | Drawings provided | Closed | Agreed complete
Commitments Register - provide copy and dashboard when available | 2022-09-01 | TT/RL | Open | Advised by RL at Oct 2022 meeting this was still outstanding. Update provided at Nov 2022 meeting | TBD March meeting | Open
Bus Shelter at Croall Place - provide details for location decision | 2022-09-01 | TT/RA | Open | Response given does not provide requested detail | Response previously provided and does not change, location agreed with Public Transport and JCD | Closed | Agreed complete
Follow up with Lothian Buses regarding delays to buses in Leith | 2022-10-01 | CC/HT | Open |  | CCTT to raise issues direct with Lothian Busses | Open | Suggest close as no further action from TT expected
Confirm location of trees in planters along the Trams route during walk throughs | 2022-10-01 | CCTT/TT | Open |  | TBD March meeting | Open
Confirm schedule for handover of sections of Trams route | 2022-10-01 | TT/RA | Open |  | SC2 provided | Closed | Do not agree that this can be closed. The original schedule for SC2 handover has not been met. Do you have an updated schedule?
Improve reporting of quality issues and their closure | 2022-10-01 | TT/RA | Open |  | Included on dashboard | Closed | Agreed complete
Arrange walk throughs of Trams Routes with CC members | 2022-10-01 | TT/RA | Open | NTBCC, LHNCC and LCCC complete | Completed last year | Closed | Agreed complete
Provide response to the isues highlighted in walk throughs | 2022-11-01 | TT/RA | Open | Also raised at December 2022 meeting. Response provided to be discussed at March 2023 meeting | Completed | Open | Suggest close as final CCTT comment now provided
Contact CEC Lighting regarding lack of lighting on Ocean Drive | 2022-12-01 | TT/RA | Open |  | Completed - ETYN street lighting installation ongoing | Closed | Do not agree that this can be closed. CC/JM to provide additional detail
Provide copy of TT response to Road Safety Audit (and if possible the RSA) | 2022-12-01 | TT/RA | Open |  | TBD March Meeting | Open
Provide summary fo discussions from meeting about defect management, etc. | 2022-12-01 | CC/HT | Open |  | TBD March Meeting | Open
Follow up with Lothian Buses regarding continued use of diversions | 2022-12-01 | TT/RL | Open |  | Completed | Open | Suggest close as no further action from TT expected
Include reporting of hard landscaping progress in CCTT reports | 2022-12-01 | TT/CW | Open |  | TBD March meeting | Open
Provide copy of Commitments Register | 2023-02-01 | TT/RA | Open |  | RL/TT to determine if GDPR would prevent sharing register | Open
Improve reporting of progress on landscaping work on dashboard | 2023-02-01 | TT/CW | Open |  | TBD March meeting | Open | Suggest close as duplicate action
Arrange lessons learned meeting for CCTT members | 2023-02-01 | TT/RL, CC HT | Open |  | TBD March meeting | Open | Doodle poll to be issued to confirm date for lessons learned meeting
Issue overall timeline for Project showing key milestones | 2023-02-01 | TT/CW | Open |  | TBD March meeting | Open | Suggest close: timeline provided by Rob Leech by email
Investigate options for mitigation of "Authority to Work" costs | 2023-02-01 | TT/CW | Open |  | TBD March meeting | Open | Suggest close as no further action from TT expected
Provide update on progress of section completion handovers | 2023-02-01 | TT/RA | Open |  | SC2 provided | Closed | Do not agree that this can be closed. The original schedule for SC2 handover has not been met. Do you have an updated schedule?
Check reasons for missing lights on some OLE poles | 2023-03-01 | TT/RA | Open
Investigate track slab mastic issues | 2023-03-01 | TT/SJ | Open