## Timeline
Trams to Newhaven Timeline
Date | Activity | Notes
2017 | Updated outline business case approved by Council
Procurement process starts
2018 | Procurement of ISC and SPC contractors
Final Business Case preparation
2018-11-01 | CCTT Formal meetings commence
19 Mar – 29 Apr2018 | First round of consultation
2018-08-28 | Leith traders consulted on Support for Business package
1 Oct – 11 Nov 2018 | Second round of consultation – you said we did | Link to summary report.
2019-03-01 | Final Business Case approved by Council | Further information
2019-03-01 | ISC and SPC contracts awarded | Further information
2019-03-01 | Early Contractor Involvement Period begins
2019-05-01 | Site investigation works begin along the route | Further information
2019-11-01 | First access letter issued to residents (Constitution Street)
2019-11-04 | Meet the team event (Constitution Street) | Further information
2019-11-18 | Works begin on Constitution Street | Further information
2019-11-18 | Leith Walk enabling works start | Further information
2020-01-27 | Meet the team event (Ocean Terminal) | Further information
2020-02-10 | First access letter issued (Newhaven - Melrose Drive) | Further information
2020-02-01 | Lothian Buses announce service diversions
2020-02-21 | First access letter issued (Leith Walk) | Further information
2020-03-24 | COVID 19 - lockdown announced by Government
2020-03-25 | COVID 19 - project shutdown | Further information
2020-05-29 | Site preparation works for reopening | Further information
2020-06-12 | Project reopening | Further information
2020-07-15 | COVID 19 - pubs, restaurants and cafes open
2020-08-14 | COVID 19 - hospitality venues to record contact details
2020-09-22 | COVID 19 - new restrictions on hospitality venues introduced
2020-10-07 | COVID 19 - Hospitality – 6am – 6pm for indoors pubs to close except takeaway
2020-10-19 | Progress to date update | Further information
2020-11-06 | Updated Business Case (COVID 19) | Further information
2020-11-19 | First rail tracks installed | Further information
2020-11-24 | COVID 19 - Limited relaxation of rules for Xmas announced
2020-12-19 | COVID 19 - Tightening of restrictions announced for Xmas
2020-12-26 | COVID 19 - Scotland to level 4 - all hospitality and leisure venues close
5 Jan 2021 | Construction restart | Further information
2021-01-28 | Stevedore Place landscaping design update | Further information
2021-02-28 | Changes to cycleway provision on Leith Walk | Further information
2021-04-02 | COVID 19 - Stay at home restrictions lifted
2021-04-06 | Start of FoTW tram stop construction | Further information
2021-04-26 | COVID 19 - Scotland to level 3 - hospitality reopens
2021-05-14 | COVID 19 - Scotland to level 2
2021-05-21 | Leith Walk cycleway update | Further information
2021-06-01 | Closure of Elm Row | Further information
2021-06-10 | First drone footage | Further information
2021-07-15 | Extension of site to Coatfield Lane | Further information
2021-08-02 | Extension of site at FoTW | Further information
2021-08-03 | Changes to traffic management on Leith Walk | Further information
2021-08-18 | Opening of Halmyre Compound site | Further information
2021-10-22 | Changes to Leith Walk traffic management | Further information
2021-11-23 | Two year look back | Further information
2021-11-26 | Notification of building fixings installation | Further information
2021-12-08 | New drone footage showing progress | Further information
2021-12-17 | First access letter issued (Queen Charlotte Street - Coatfield Lane) | Further information
2022-01-05 | Changes to Leith Walk traffic management | Further information
2022-01-05 | Site extension - Picardy Place to York Place | Further information
2022-01-25 | Robert Burns Statute returns | Further information
2022-01-27 | Works starting - east side of Leith Walk | Further information
2022-02-03 | Construction start at York Place | Further information
2022-02-04 | Works to start on Melrose Drive | Further information
2022-02-17 | Construction start - Rennie's Isle - Tower Place | Further information
2022-02-18 | Reinstatement works at Elm Row to start | Further information
2022-03-25 | Progress to date update, including programme update | Further information
2022-03-28 | York Place works completed | Further information
2022-04-01 | 2-way traffic back on Lindsay Road | Further information
2022-05-26 | Traffic management changes - Picardy Place - Annandale Street | Further information
2022-06-01 | Traffic management changes - Pilrig Street - London Road | Further information
2022-06-13 | Traffic managent changes - Pilrig Street - Annandale Street | Further information
2022-06-20 | Updated drone footage | Further information
2022-07-11 | Largest concrete pour to date - Rennie's Isle | Further information
2022-07-13 | Pilrig Street - London Road reopens, including programme update | Further information
2022-08-17 | London Road clock returns to Elm Row | Further information
2022-08-18 | Changes to traffic management between Annandale Street and York Place | Further information
2022-09-05 | Closure of Brunswick Street junction | Further information
2022-09-28 | Article on simulator for driver training including programme update | Further information
2022-10-18 | FoTW traffic management changes | Further information
2022-10-19 | Annandale Street - Picardy Place traffic management changes | Further information
2022-10-28 | Changes to Brunswick Road junction | Further information
2022-11-21 | London Road junction re-opens, banned left hand turn introduced | Further information
2022-11-25 | FoTW - Manderston Street traffic management changes | Further information
2022-11-29 | Overhead line out of hours working | Further information
2022-12-20 | Final tram track laid | Further information
2022-12-21 | London Road left hand turn mitigation measures | Further information
2022-12-23 | 2022 update and progress | Further information
2023-02-03 | Two way traffic to Leith Walk, programme update and electrification | Further information
2023-03-13 | Testing and commissioning starts on route | Further information
2023-03-13 | First trams on route | Further information
2023-03-17 | Leith Walk remedial works | Further information